## Sheet1
Sprint Logs
Sprints | Description
Sprint 1: Create Graphical user interface using windows forms | Use Visual Studio to create form, Create relevant code for the form, create the relevant fields in the form.
Sprint 2: Implement News API to the artefact | Collect the relevant news API key, add to the artefact, implement with the GUI, use C#.
Sprint 3: The graphical user interface needs to show the different headlines and regions of news | Use the News API in the artefact, create the relevant code to do this, use C#, connect this feature to the GUI.
Sprint 4: Switch from C# to python to continue with artefact for the Spotify API | Use python to impement the Spotify API
Sprint 5: Test the Artifact | Run the artifact and make sure it compiles with the corresponding news and music
Product Backlog | Story Points - 1SP = 1 Hour | Priority Points 1-10
Artefact needs to compile spotify playlist from news | 1 | 10
Artefact needs to communcate with Spotify API to create music playlist | 3 | 9
Implement the News API into the artefact | 1 | 9
Artefact needs to associate words from news headlines and music | 4 | 8
The artefact needs to show the different headlines and regions of news | 3 | 7
Create a Graphical User Interface using windows forms | 1 | 5
Groomed Product backlog | Story Points - 1SP = 1 Hour | Priority Points 1-10
Create a Graphical User Interface using windows forms | 1 | 10
Implement the News API into the artefact | 3 | 9
The graphical user interface needs to show the different headlines and regions of news | 1 | 9
Use python for the spotify API (because Spotify API was discontinued in C#) | 4 | 8
Test the artefact for the spotify playlists | 3 | 7

## Sheet2
Artefact needs to communcate with Spotify API to create music playlist | 3 | 9
Create method
Implement the News API into the artefact | 1 | 9

## Sheet3
Sprint Start Date | 2019-10-04 |  | Day of the Sprint | Forecast | Target | Actual
|  |  | 0 | 16 | 24 | 20
Sprint End Date | 2019-10-15 |  | 1 | 15 | 21.6 | 18
Working Days | 8 |  | 2 | 13 | 19.2 | 15
Work Hours Per Day | 3 |  | 3 | 12 | 16.8 | 12
Total Available Hours | 24 |  | 4 | 9.6 | 14.4 | 10
Productive Hours | 19.2 |  | 5 | 7.2 | 12 | 7.5
Average Daily Productive Hours | 2.4 |  | 6 | 4.8 | 9.6 | 4
|  |  | 7 | 2.4 | 7.2 | 2
|  |  | 8 | 0 | 4.8 | 0
Available Effort
Day of Sprint | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Total Effort | 20
1 | 1 | 1 | 1 | 1 | 4 | 16
2 | 1 | 1 | 1 | 1 | 4 | 8
3 | 2 | 1 | 1 | 0 | 4 | 4
4 | 0 | 0 | 0 | 0 | 0 | 4
5 | 0 | 0 | 0 | 0 | 0 | 4
6 | 0 | 0 | 0 | 0 | 0 | 4
7 | 0 | 0 | 0 | 0 | 0 | 4
8 | 1 | 1 | 1 | 1 | 4 | 0
total | 5 | 4 | 4 | 3 | 16