## Sheet1
Sprint Logs
Sprints | Description
Sprint 1: Create Graphical user interface using windows forms | Use Visual Studio to create form, Create relevant code for the form, create the relevant fields in the form.
Sprint 2: Implement News API to the artefact | Collect the relevant news API key, add to the artefact, implement with the GUI, use C#.
Sprint 3: The graphical user interface needs to show the different headlines and regions of news | Use the News API in the artefact, create the relevant code to do this, use C#, connect this feature to the GUI.
Sprint 4: Switch from C# to python to continue with artefact for the Spotify API | Use python to impement the Spotify API
Sprint 5: Test the Artifact | Run the artifact and make sure it compiles with the corresponding news and music
Product Backlog | Story Points - 1SP = 1 Hour | Priority Points 1-10
Artefact needs to compile spotify playlist from news | 1 | 10
Artefact needs to communcate with Spotify API to create music playlist | 3 | 9
Implement the News API into the artefact | 1 | 9
Artefact needs to associate words from news headlines and music | 4 | 8
The artefact needs to show the different headlines and regions of news | 3 | 7
Create a Graphical User Interface using windows forms | 1 | 5
Groomed Product backlog
Create a Graphical User Interface using windows forms
Implement the News API into the artefact
The graphical user interface needs to show the different headlines and regions of news
Use python for the spotify API (because Spotify API was discontinued in C#)
Test the artefact for the spotify playlists

## Sheet2
Artefact needs to communcate with Spotify API to create music playlist | 3 | 9
Create method
Implement the News API into the artefact | 1 | 9

## Sheet3
Sprint Start Date | 2019-10-04 |  | Day of the Sprint | Forecast | Target | Actual
|  |  | 0 | 19.2 | 24 | 16
Sprint End Date | 2019-10-15 |  | 1 | 16.8 | 21.6 | 13.4
Working Days | 8 |  | 2 | 14.4 | 19.2 | 12.4
Work Hours Per Day | 3 |  | 3 | 12 | 16.8 | 9
Total Available Hours | 24 |  | 4 | 9.6 | 14.4 | 9
Productive Hours | 19.2 |  | 5 | 7.2 | 12 | 6
Average Daily Productive Hours | 2.4 |  | 6 | 4.8 | 9.6 | 4
|  |  | 7 | 2.4 | 7.2 | 2
|  |  | 8 | 0 | 4.8 | 0
Day of Sprint | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Total Effort
1 | 1 | 1 | 1 | 1 | 4
2 | 1 | 1 | 1 | 1 | 4
3 | 2 | 0 | 1 | 1 | 4
4 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0
8 | 1 | 1 | 1 | 1 | 4
total | 5 | 3 | 4 | 4 | 16